## Arkusz1
|  | 2017 | [11 empty] | 2018 | [11 empty] | 2019
PHASE | TASK | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
1) PHASE 1 - DATA SIMULATION AND PRE-PROCESSING OF THE DETASETS | 1.1) Milestone 1 - Recruitment of the PhD student done
1.2) Microarray data simulation
1.3) Milestone 2 - Datasets ready
1.4) Determination of correlation structure for datasets from public repositories
2) PHASE 2 - DEVELOPMENT OF THE NOVEL TESTS STATISTICS | 2.1) Creation of the novel test statistics for microarray data
2.2) Modification of the proposed statistical test based on other dependency measures
2.3) Determination of gene co-expression network for different dependency measures¦
2.4) Determination of the statistical model based on network adjacency matrix
2.5) Creating the test statistics taking into account adjacency matrix
2.6) Milestone 3 - novel algorithms for gene selection for microarray data ready
2.7) Conducting research referred to 3.1 - 3.5 based on RNA-seq data
2.8) Milestone 4 - novel algorithms for gene selection for RNA-seq data ready
2.9) Checking the properties of the novel statistics
3) PHASE 3 - THE EVALUATION OF THE RESULTS AND THE COMPARATIVE ANALYSIS | 3.1) The evaluation of the results with the comparative analysis
3.2) Milestone 5 - report from comparative analysis ready
4) PHASE 4 - SUMMARIZATION OF THE RESEARCH AND DISSEMINATION OF THE RESULTS | 4.1) Milestone 6 - publication of the software and publications in journals

## Arkusz2
1) PHASE 1 - Data simulation and pre-processing of the datasets | 2017-01-01 | 2017-07-31
1.1) Milestone 1 - Recruitment of the PhD student | 2017-02-01 | 2018-02-28
1.2) Microarray data simulation | 2017-01-01 | 2017-05-31
1.3) Milestone 2 - Datasets ready | 2017-06-01 | 2017-06-30
1.4) Determination of correlation structure for datasets from public repositories | 2017-03-01 | 2017-07-31
2) PHASE 2 - DEVELOPMENT OF THE NOVEL TESTS STATISTICS | 2017-06-01 | 2018-12-31
2.1) Creation of the novel test statistics for microarray data | 2017-06-01 | 2017-12-31
2.2) Modification of the proposed statistical test based on other dependency measures | 2018-01-01 | 2018-04-30
2.3) Determination of gene co-expression network for different dependency measures¦ | 2017-09-01 | 2018-01-31
2.4) Determination of the statistical model based on network adjacency matrix | 2018-02-01 | 2018-03-30
2.5) Creating the test statistics taking into account adjacency matrix | 2018-04-01 | 2018-07-30
2.6) Milestone 3 - novel algorithms for gene selection for microarray data ready | 2018-07-01 | 2018-07-30
2.7) Conducting research referred to 3.1 - 3.5 based on RNA-seq data | 2018-05-01 | 2018-10-31
2.8) Milestone 4 - novel algorithms for gene selection for RNA-seq data ready | 2018-11-01 | 2018-10-31
2.9) Checking the properties of the novel statistics | 2018-11-01 | 2018-12-31
3) PHASE 3 - THE EVALUATION OF THE RESULTS AND THE COMPARATIVE ANALYSIS | 2019-01-01 | 2019-06-30
3.1) The evaluation of the results with the comparative analysis | 2019-01-01 | 2019-07-31
3.2) Milestone 5 - report from comparative analysis ready | 2019-07-01 | 2019-07-31
4) PHASE 4 - SUMMARIZATION OF THE RESEARCH AND DISSEMINATION OF THE RESULTS | 2019-07-01 | 2019-12-31
5) Milestone 6 -publication of the software and publications in journals | 2019-12-01 | 2019-12-31